Program Name

Annual Mulch Fundraiser

Purpose of the program

The Annual Mulch Fundraiser is the largest fundraiser conducted by our troop. The troop raises funds annually for participating scouts to enable them to go to summer camp and high adventure camp. Mulch is ordered from a third party and sold to neighborhoods (2-3 zip codes) around the troop meeting venue, Our Saviors Way Lutheran Church or OSWLC. The entire troop’s participation is highly encouraged and makes it a profitable operation.

This is a Troop-wide event, and all scouts are eligible for earning against actual hours served, which are converted into proceeds from the fundraiser into their Scout Accounts. The funds are automatically added to the individual scout account balances of participating scouts and scouters based on the hours that they volunteer. Any unused funds revert to the Troop. Funds cannot be pulled out from the scout account.

Benefits of the program

- The mulch program provides the entire troop with a great purpose to serve the community.

- It enables the Troop to earn funds for summer camp and activities such as high adventure.

- It provides the scouts and the scouters a great way to keep their body physically strong.

- It provides learning opportunities through youth-adult and older-younger scout associations.

- It provides practical lessons in distribution logistics planning and execution.

- Our bags are 50% larger compared to big box stores for similar pricing!

- Free delivery to customer homes where the bags are stacked neatly within their driveway!

- It showcases to Cubs feeder programs a great program that our Troop offers.

- Participating Scouts and adults get a free mulch T-shirt custom designed by scouts!

Frequency of Occurrence

Annual

Schedule

- Mulch Event Planning Start – November of every year.

- Mulch Flyer Distribution – Last two weekends of February of every year (rough estimate).

- Mulch Delivery – Last two weekends of March or first two weekends of April every year (rough estimate).

Roles and Responsibilities

- Mulch Coordinator

- Order Coordinator

- Website Coordinator

- Flyer Distribution Coordinator

- Rental Equipment Coordinator

- School Coordinator

- Food Coordinator

- Food Preparers

- T-Shirt Coordinator

- Site Safety Coordinator

- Truck Driver

- Navigator Car Driver

- Crew Drivers

- Forklift Driver

- Scout Crew Leads

- Scouts

Processes

Wrap-up

Mulch Distribution

Order Placement

Flyer Distribution

Planning

Initial Planning Kick-off

- Initial Planning Kick-off (November)

  - The Mulch Coordinator identifies and confirms flyer and mulch delivery dates with the committee.

  - The Mulch Coordinator creates and sends a Google forms-based Mulch Commitment Survey for mulch and flyer delivery sign-up.

  - Sample Google Forms survey: https://docs.google.com/forms/d/e/1FAIpQLSeDP5zglVhVZC_G8LiO5rAB7MvoqWbXjAD0Rr1dgP3u8WyXKw/viewform?pli=1

  - The Mulch Coordinator repeatedly emphasizes early commitments from parent and scout volunteers!

  - The Mulch Coordinator sends a troop email announcing the date for the Initial Planning Kick-off containing the mulch sign-up survey link.

  - The email and Band App messaging has the following format (or similar):

Attention all scouts AND parents:

Announcing the kickoff of Troop 2970's <Year> Mulch Fundraiser!

The Mulch Planning Kickoff Meeting will be held on January <Date> at 7:30pm Thursday. We will be holding a Mulch meeting at the normal Troop meeting to go over the mulch delivery program and the planning/distribution logistics and to make sure everyone is signed up for a job.

Mulch Flyer Delivery will be held on the following <Dates>. Please watch for further announcements for time and location.  Participation is open to all scouts and adults.

Mulch Signup:  Attached you will find the Mulch <Year> commitment Google form. Please complete the survey by <January Date>.  <Insert Survey Link>

IMPORTANT:  Every participating scout should have at least one parent that is participating for the weekends, either distributing flyers, moving mulch, and/or helping with food preparation.

Please be sure to read the commitment form carefully and submit the survey as soon as possible.

  - The Mulch Coordinator conducts the Mulch Planning kick-off meeting:

    - Presents the program details and benefits,

    - Urges attendees to complete the survey early, notifying late entries or no survey entry will not earn money

    - Asks for volunteers, and

    - Requests people to mark the schedule in calendars.

  - Mulch Coordinator obtains survey responses and plans the following:

    - Identifies headcount of adult and scout commitments,

    - Food preferences,

    - T-shirt sizes,

    - Role-based volunteers

  - Mulch Coordinator works with volunteers confirming their roles, conducting kick-offs of respective planning activities, and assigning jobs and instructions.

  - Mulch Coordinator creates and maintains a master roster of volunteers with assigned roles and contact information.

- Planning (November - February)

  - Money Earning Application

    - The Mulch Coordinator or a designated committee member submits a money earning application to Scouts BSA using the form provided: https://filestore.scouting.org/filestore/pdf/34427.pdf

    - The Mulch Coordinator will need to get a written approval of the form/signed copy from the concerned Scouts BSA point of contact before the mulch program can begin execution.

    - Here is a sample of a money earning application.

  - T-shirt Design

    - The T-Shirt Coordinator announces T-shirt Design at the troop meeting 2 months in advance.

    - The SPL or designate compiles T-shirt design, adjudicates and picks a design.

    - The T-Shirt Coordinator places orders based on T-shirt sizes received in the commitment survey.

    - The T-Shirt Coordinator receives the T-shirt bulk order and distributes before scheduled delivery.

    - The T-Shirt Coordinator manages a sign-in form to distribute and account for the T-shirts.

  - Website & Flyer Design and Advertising

    - The Website Coordinator updates the troop mulch delivery website content for advertising and marketing.

    - Sample webpage: https://troop2970.com/mulch-fundraiser/

    - The Mulch Coorindator or designate designs the flyer for the upcoming flyer delivery. A sample of the past year’s flyer is provided below.

  - Site Safety Briefing

    - The Site Safety Coordinator announces and schedules a mandatory safety briefing at one of the troop meetings, before mulch delivery.

    - The Site Safety Coordinator plans on conducting safety briefings for all participating volunteers before mulch delivery.

  - School Use Co-ordination

    - Our troop receives and distributes mulch orders from suitably identified school parking lots.

    - In the past, our troop has used the parking lots of Eagle Ridge Middle School, Park View High School, Potomac Falls High School, Sterling Elementary School, and Stone Hill Middle School.

    - The choice of the school(s) depends on the zip codes covered for flyer and mulch delivery and the availability of the lot per the LCPS calendar.

    - A video of how to request the use of a public school parking lot is available here.

    - To use a public facility such as the parking lot, the troop needs to be registered with LCPS as a ‘Community Use Organization’. Our troop is already registered as one. This linked LCPS website has all the details.

    - The School Coordinator submits the use request form directly to the school using the template.

    - A use request form sample is provided below.

  - Supplier and Product Co-ordination

    - The Order Coordinator orders the mulch based on the amount demanded by the customers.

    - The troop has in the past purchased mulch from JK Enterprise Landscape Supply.

    - The mulch supplier delivers ordered mulch to the troop designated school parking lot(s).

    - Grades of bagged mulch that troop offers are: High Quality Double Shredded Hardwood & Color Enhanced Mulch

      - Natural Color

        - 3 Cubic Ft. Bag of Double

        - Shredded Hardwood Mulch

      - Black Color

        - 2 Cubic Ft. Bag of Black

        - Color Enhanced Mulch

    - The Order Coordinator puts the mulch order contract in place working with the mulch supplier. Provided below is a sample of such a contract.

    - Tax Exemption

      - The money earned from mulch sale is not taxable if it goes towards scouting activities.

      - Many times, the vendors do not provide this tax break, and that is fine.

      - If a vendor agrees to exempt the troop from paying sales tax, the Order Coordinator works with the Chartering Organization’s Representative to create a tax-exempt letter and provides it to the vendor.

      - The letter to the vendor is in the following format.

Date:  <Insert Date>

To Whom It May Concern,

This letter is to certify that Our Savior's way Lutheran Church (OSWLC) in Ashburn, Virginia is the official sponsor, known as the Charter Organization, for Boy Scout Troop 2970, and that Troop 2970 is part of the Church's youth outreach program.  OSWLC is a 501(c)(3) charitable non-profit organization, and its tax ID# is 91-1822951.

Regards,

Ed Yarbrough

Charter Organization Representative

Troop 2970 /Our Savior’s Way Lutheran Church

      - The Order Coordinator also submits the ST-13A form Commonwealth of VA Sales and Use Tax Certificate of Exemption to the vendor, a sample of which is provided below.

  - Food Co-ordination

    - The Troop will plan to provide food for the volunteers.

    - Vegan and vegetarian options will be included.

    - The Food Coordinator may conduct a troop survey to include appropriate food options.

    - The Food Coordinator will prepare a budget for food expenses based on available volunteers.

    - The Food Coordinator will sign up food preparation volunteers and residences willing to use kitchens for cooking.

  - Truck and Equipment Rental

    - Equipment Rental Coordinator coordinates rental equipment with Penske, Sterling VA

    - The quantity of equipment and trucks are determined based on the volunteer sign-ups and area planned for coverage.

  - Flyer distribution Planning

    - Scouts and parent volunteers deliver mulch flyers to the identified area customers/houses on two Saturdays in early March.

    - The Flyer Distribution Coordinator designs and prints the flyers based on the estimates for the number of houses to cover for the identified zip codes, and volunteers available.

    - The flyers will have prices and a link to the Troop Mulch Advertisement web page.

    - For tight alleys and one-way streets, ask residents through the flyer, to note where they want delivered by the box truck, while they place their orders.

    - The Flyer Distribution Coordinator plans the route guidance maps and makes printouts based on the planned area to be covered, orders, number of cars, and volunteers estimated to attend.

    - The Flyer Distribution Coordinator plans the number of full days that would be required for covering targeted housing areas, based on the volunteer sign-up.

    - Prepare maps that clearly show street names and rough estimates of houses to be covered.

    - Correctly estimate the flyer quantity to be printed and print extra to avoid getting runout of printouts.

    - At one of the troop meetings, before the beginning of the actual flyer delivery, the Flyer Distribution Coordinator details the flyer delivery logistics to the troop. (See below for Flyer Distribution Kick-off activity details).

    - The flyer delivery logistics include the date, time, venue for assembly, driver assignments, work expectations, communication protocols etc.

    - The Mulch Coordinator uses the same route guidance maps to deliver mulch.

    - Once customers submit their orders, the Mulch Coordinator compiles the orders received and organizes mulch delivery.

  - Reminders

The Mulch and other Coordinators should send constant reminders using emails and Band App for the following events:

    - Mulch Planning Kick-off Meeting

    - Mulch Commitment Survey Completion

    - T-Shirt Design Completion and Order Completion

    - Website Design Completion

    - School Parking Lot Request Completion

    - Food preparation sign-ups

    - Flyer Distribution Kick-off Meeting

    - Flyer Distribution Event

    - Mulch Delivery Kick-off Meeting

    - Mulch Distribution Event

- Flyer Distribution (February - March)

  - Flyer Distribution Kick-off

    - Conduct a Flyer Distribution Kick-off 1-2 weeks before the flyer distribution at the troop meeting.

    - Complete scheduled Flyer distribution minimally 1 month before mulch distribution and early in the year. This prevents other troops and vendors from making their moves before us and spoiling our efforts at selling mulch to residents.

    - Check neighborhoods for overlaps with other troop delivery.

    - Enable SPL and PLs to take active participation in the kick-off meeting with roles to play.

    - Walkthrough the following with the flyer distribution volunteer crew:

      - Schedule: Walkthrough the days and timings when flyers will be distributed. Communicate the venue and time of assembly expectations for all volunteers.

      - Weather: Check the weather and confirm the plan.

      - Dress Code: Dress according to the weather. Wear a hat or a Class B to denote Scouting activity. Dress in layers.

      - Maps: Prepare area maps and give an idea of the area to cover. Plan Black mulch routes separate from regular mulch routes and do not mix the two.

      - Roles and Responsibilities

      - Doorway and other etiquettes:

        - Show up on time.

        - Be respectful of property, don’t walk on the lawns and grass and use the pathway.

        - Describe how to hang the flyer in the doorway and entrance of houses.

        - Wish homeowners if you see them.

        - Describe dos and don’ts based on scenarios for flyer distribution.

      - Lunch and break schedule: Communicate the lunch and break schedule.

      - Crew formation:

        - Sign-up driving parent volunteers.

        - Divide the scouts equitably per crew where older scouts should help younger scouts.

        - Determine crew size, number of crews/vehicles heading for distribution.

      - Ground Communication: Obtain mobile numbers from driving and parent volunteers and create a group contact handle for ground communication during flyer distribution.

  - Flyer Distribution

    - On the designated flyer delivery dates, troop volunteers assemble before the designated time at the designated venue communicated by the Mulch Coordinator.

    - Flyer Distribution Coordinator provides sign-in sheet that volunteers use to sign-in and out.

    - The Flyer Distribution Coordinator provides instructions and route guidance to all volunteer attendees.

    - A Food Coordinator arranges breakfast/lunch as appropriate, for the volunteer attendees.

    - The Flyer Distribution Coordinator distributes adequate flyers to each volunteer vehicle.

    - The Flyer Distribution Coordinator will equitably distribute Scouts in volunteer vehicles with a good mix of younger and older scouts so that younger scouts can watch and learn under older scouts.

    - All volunteers are expected to follow through on their commitment to their schedules.

    - Volunteers making any schedule changes either before or during the flyer distribution need to communicate the change to the Mulch Coordinator.

    - Participants are expected to work all day until the tasks for the day are completed.

    - Sign-in and Sign-out management: The Mulch Coordinator uses a Sign-in/Sign-out sheet for volunteers to sign-in and out, in-person, for flyer distribution. A sample template is provided below. Prepare Sign-in and out sheets. Designate a volunteer to oversee the signing in and out at the designated spot for all distribution days. Everyone volunteering should be singing-in and out with the correct timing.

    - The Flyer Distribution Coordinator conducts retrospective and lessons learned and disseminates notes.

- Customer Order placement, receipt, and storage (March-April)

  - Customers place orders for mulch up until a particular date using the details provided in the flyer.

  - The Order Coordinator maintains the customer and order details in an Excel Spreadsheet.

  - Order details include Invoiced Quantity, Invoiced Amount, Order Date/Time, Customer Home Type, Shipping Community, Shipping Name and Address, Customer Phone, Customer Email, Order Source, Billing Name and Address

  - The bulk orders (Color Enhanced bags and Natural bags are offered) are delivered to the school.

  - Order Coordinator communicates with mulch vendor to deliver Mulch to the school Friday night, after school is over. School parking lots are available by 5:00 PM Friday.

  - Order Coordinator communicates the number of bags/pallets ordered, by mulch type (natural or colored), to the Mulch Vendor.

- Mulch Distribution (April)

  - Mulch Distribution Kick-off

    - Conduct a Mulch Distribution Kick-off one week before the mulch distribution at the troop meeting.

    - Enable SPL and PLs to take active participation in the kick-off meeting with roles to play.

    - Walkthrough the following with the mulch distribution volunteer crew:

      - Venue: Communicate the venue and the exact address and location where volunteers are expected to assemble and operate from.

      - Schedule: Walkthrough the days and timings when mulch will be distributed.

      - Weather: Check the weather and confirm the plan.

      - Bring a water bottle.

      - Dress Code:

        - Dress according to the weather.

        - Wear a hat or a Class B or a scout appropriate apparel to denote Scouting activity.

        - Dress in layers.

        - Wear boots. No flip-flops.

        - Set expectations that dress will get stained, and everyone will get messy.

      - Maps: Prepare area maps or give an idea of the area to cover. Plan Black mulch routes separate from regular mulch routes and do not mix the two.

      - Roles and Responsibilities

      - Doorway and other etiquettes:

        - Show up on time.

        - Be respectful of school and homeowner property.

        - Don’t walk on the lawns and grass and use the pathway.

        - Verify house numbers.

        - Describe how to stack the mulch sacks per specific homeowner or generic instructions provided by the Mulch Coordinator.

        - Take good care of the mulch bags and avoid tearing them!

        - Stack up to five bags. Don’t throw them!

        - Wish homeowners if you see them.

        - Describe dos and don’ts based on scenarios for mulch distribution.

      - Lunch and other break schedule: Communicate the lunch and any break schedule.

      - Crew formation:

        - Sign-up driving parent volunteers.

        - Determine crew size.

        - Divide the scouts equitably (older scouts helping younger scouts),

        - Determine number of crews/vehicles heading for distribution.

        - Assign a Scout crew lead. Rotate the Scout Crew Lead assignments every day so everyone gets a chance.

      - Ground Communication:

        - Obtain mobile numbers from driving and parent volunteers.

        - Create a group text handle for ground communication during flyer distribution days.

        - Charge your phones ahead of time.

        - All volunteers store the Mulch Coordinator phone contact.

      - Forklift and Driver Safety Briefing:

        - Provide a safety package and briefing to volunteer forklift and mulch truck drivers.

        - Forklift and Truck Drivers should sign next to their names after listening to the communications.

        - Mulch pallets weigh 2000 pounds (1 ton). Be careful around pallets wherever they are.

        - Do not play on the pallets. They are unstable, will fall over, crush someone, and make a mess for everyone else to clean up.

        - Be aware of your surroundings. Forklifts move fast.  Truck routes go in and out of site.

        - No riding on the Forklift.

        - No riding in the back of the truck.

        - Using equipment for any purpose other than its intended use is not permissible.

        - Be careful taking turns. Go slow as mulch pallets are unstable.

        - Be careful backing into driveways. Know your surroundings. Be aware of the gradient slope of the driveway. Take help from the Car Navigator Driver.

        - Only put 6 pallets in a truck, no more.

        - Truck Drivers will be held responsible for all truck and property damage.

        - If one causes damage to the truck, let the Rental Equipment Coordinator know immediately. Rental Equipment Coordinator will work with rental agreements and rental company.

        - If one causes damage to any property, let the Mulch Coordinator know immediately.

        - If involved in an accident or a flat tire, review the rental agreement and report immediately and appropriately, including 911.

    - Sign-in and Sign-out management: The Mulch Coordinator uses a Sign-in/Sign-out sheet for volunteers to sign-in and out, in-person, for flyer distribution. A sample template is provided above. Prepare Sign-in and out sheets. Designate a volunteer to oversee the signing in and out at the designated spot for all distribution days. Everyone volunteering should be singing-in and out with the correct timing.

  - Food preparation and serving

    - Food Coordinator sends and compiles food sign-ups survey email for mulch delivery.

    - Food Coordinator sends and compiles fun food preparation crew volunteering sign-up for mulch delivery.

  - Equipment Rental

    - Trucks – Penske – Sterling

    - Pallet Jacks – Sunbelt – Sterling

    - Forklifts – Sunbelt – Sterling

    - Dumpster – 30 Yard – School

    - Truck Drivers provide a copy of your driver’s license to the Equipment Rental Coordinator.

    - The truck rental is considered a business rental and we are required to purchase Penske insurance. We have purchased all of the insurance options.

      - Limited Damage Waiver (LDW) – Protects the TRUCK - $1000 deductible. LDW coverage provides protection for the loss or damage to the vehicle during the term of the rental. The coverage relieves you of financial responsibility should any loss or damage occur to the truck or towing equipment except if the vehicle or equipment is used in a manner that violates the terms of the rental agreement.

      - Supplemental Liability Insurance (SLI) – Protects the renter. SLI protects the renter and any listed authorized drivers against claims made by a third party for bodily and/or property damage sustained as a result of an accident while you are operating a Penske truck. This coverage is excess over the underlying insurance specified within your signed rental agreement up to $1,000,000. Renters and all drivers must be 21 years of age to purchase.

      - Liability - You are protected to the limits of liability up to the requirements of financial responsibility law or other applicable statute of the state or municipality in which the accident occurred.

  - Forklift Operations and Pallet Loading

    - Forklifts and pallets of mulch are carried in the truck using forklifts from the school parking lot.

    - 2 Forklift operators will be needed.

    - 2 adults in each truck needed to load and unload along with 3-4 trucks. This includes one driver.

    - Adults help load pallets onto the truck so that optimum pallets fit the truck interior space.

  - Truck Driving

    - The truck drivers are not done until all the mulch is delivered, and the site is 100% clean.

    - Truck drivers are responsible for the entire crew that goes with the truck.

    - Truck Drivers are utmost responsible for the safety of the crew and the operation.

    - Truck Drivers bring a push broom and utility knife.

    - Truck Drivers get a duct tape from the troop.

    - Truck Drivers pick up the truck between 3:00-5:00 PM the previous day as the rentals close at 5:00 pm.

    - Truck Drivers drive the newly rented truck to the designated school parking site.

    - Truck Drivers park the truck in the designated parking/loading area.

    - Truck Drivers open the back of the truck for the next day loading.

    - Truck Drivers leave the truck unlocked and keys under the floor mat or cup holder as fork lift drivers may need to move.

    - Truck Drivers arrange for a ride home.

    - Truck Drivers arrive at the designated distribution day early/planned time and inspect the truck for any flat tires or damage.

    - Truck Drivers attend the site safety briefing provided by the Site Safety Coordinator.

    - Truck Drivers confirm Truck Driver/Car Navigator Driver roles.

    - Truck Drivers and Car Navigator Drivers pickup their routes from the Mulch Coordinator.

    - Truck Drivers head out behind the Car Navigator Driver, followed by the rest of the crew vehicles behind the truck. 1. Pilot Navigator Vehicle -> 2. Truck -> 3. Rest of the crew.

    - Scouts will ride behind the trucks in parent-driven personal vehicles, as the Truck Drivers progress on organized delivery routes.

    - At the end of the day, Truck Drivers fill up the trucks with gas before returning to the school parking lot.

  - Pilot Car Navigation

    - Car Navigator Driver is in a pilot vehicle ahead of the truck, with the route maps.

    - Car Navigator Driver obtains the route maps from the Mulch Coordinator and plans the route and area coverage in collaboration with the Truck Driver.

    - Enable Scouts to learn and help with navigation by having a scout sit in with the Car Navigator Driver.

    - Avoid going back and forth within the same coverage area. Systematically progress on coverage by optimizing gas and crew resources.

    - Use more of car navigation/GPS and less of phone navigation as you drive.

    - When one arrives at the delivery site, the Car Navigator Driver should come out of the vehicle and guide/point the truck to park at the delivery site. Truck Drivers make decisions whether to pull in, or back in or position the truck to optimize delivery.

  - Home Delivery

    - 10-12 Scouts typically ride on parent-driven vehicles with each truck.

    - Scout Crew Leads guide the crew on good etiquettes and following customer instructions.

    - Adults or larger scouts climb up the truck, unwrap the bags, and hand down from the truck to the waiting scouts.

    - Working smart, tall adults unload the pallets in the truck.

    - Move the pallets in pairs to avoid single standing pallet does not topple inside the truck and cause unnecessary headache of cleanup.

    - Stay hydrated.

    - Take food and bio break at the appropriate time of the day.

    - Be considerate of the various needs of your crew members.

  - Clean-up

    - At the last stop for each day, Truck Driver and adult volunteers can use the black mulch topper to sweep clean the truck insides. Tie the ends of the black mulch topper and dispose at the dumpster. Makes for easy cleanup.

    - At the last stop for each day, Truck Driver records the number of mulch bags left upon return to the school parking lot. Report to the Mulch Coordinator. Store the leftover bags in the front of the truck for easy pallet loading the next day.

    - Pallets do not go into the dumpster.  They take up too much space.  If the pallets are broken, Truck Drivers stack them separately to be hauled away.  Pallets make great firewood. Take broken ones home.

    - Truck Drivers clean all good pallets of trash and stack them neatly beside the dumpster.

    - After returning the school parking lot, Truck Drivers clean the trucks.

    - Truck Drivers return the pallet jacks back to the school site and keep them near the forklifts.

    - End of day, Truck Drivers return the trucks to the truck rentals and drop off the keys at the drop box available at the rental site. Report the return to the Rental Equipment Coordinator.

    - Leave no trace!

- Post-distribution wrap-up (Apr-May)

  - Leftover bags: Leftover bags may be returned or sold later or stored for future use.

  - Leftover T-shirts: Leftover T-shirts are kept by the troop for use by scouts.

  - Mulch Coordinator publicizes the Mulch Distribution accounts and resolves any Scout Account balance issues.

  - Data Compilation: Mulch Coordinator compiles data on the mulch operation for future improvements. This data includes metrics such as number of trucks used, number of active volunteers, Bags per turn, Number of turns, Number of houses delivered, Number of bags delivered, Number of Scouts volunteered etc.

  - Mulch Coordinator itemizes expenses, calculates the net profit and distribution per volunteer and creates a final income statement.

  - The Mulch Coordinator keeps all records of volunteer hours by volunteer, and points and dollars for distribution.

  - The Mulch Coordinator works with the Treasurer to expedite payments within 1-2 weeks to volunteers so that funds are available for the upcoming high adventure camps.

  - Mulch Coordinator works with all other lead volunteers to conduct retrospective, and document lessons learned.

  - Mulch Coordinator disseminates a Thank you e-mail and announcements.

  - A sample presentation is provided below.